# ALAAP

Platform Status and Path to First Local Run

What is finalised, what is built, and the milestones remaining to running the whole platform on one machine.

Prepared   11 September 2026
Repository   D:\Projects\wellness\alaap-platform
Target machine   Ryzen 9 9950X3D  ·  RTX 5070 Ti 16 GB  ·  32 GB RAM
Basis   Direct audit of the repository, not estimates. Counts exclude placeholders.

### How to read this document

Sections 1 to 3 describe what has been decided and will not change without a good reason. Sections 4 and 5 are the honest inventory: what actually runs today, and what is still an empty directory. Section 6 is the remaining path. Section 7 is what could go wrong.

Where a number is exact it comes from counting files or querying the running database. Where it is an estimate it says so. Nothing here is rounded up to look better.

## 1.  What Alaap Is

Alaap is a mental wellness platform built around one idea: that a person should be able to say the thing they cannot say anywhere else, without it costing them their name.

Four things happen on it. A person posts anonymously and receives an AI response plus replies from other people. They keep a private journal and mood record. They can book a therapist. And in a crisis, a narrow, evidenced, two-person-approved path can reach an emergency contact — and only then.

The word alaap is the opening of a raga: unmetered, unaccompanied, one voice finding what it wants to say before anything else joins in.

## 2.  Plans and Limits

Four tiers. No advertising on any of them, ever — someone who has come here for relief should not be sold to while they are in it. That constraint is what makes the free tier's limits necessary rather than greedy: the paid tiers carry the AI and infrastructure cost.

|  | Free | Interaction (₹99/mo) | Interaction Plus | Care |
| --- | --- | --- | --- | --- |
| Posts | 4 per month | Unlimited | Unlimited | Unlimited |
| Replies written | 10 per month | Unlimited | Unlimited | Unlimited |
| AI response | 1 per post | 1 per post, plus reflection prompts | Extended | Extended |
| Journal & short stories | Not available | Not available | Included | Included |
| Post expiry | 5 days | 5 days, extendable to 30 | Extendable | Extendable |
| Therapy | — | — | — | Included |

Government subsidy is planned at the full ₹99 rate rather than a reduced one, so a subsidised member's experience is identical to a paying member's and nothing on screen marks them out.

## 3.  Architecture

### 3.1  Five vaults, three databases

53 tables across six databases on three separate PostgreSQL instances. The separation is not organisational tidiness — it is what makes "no cross-vault join" structurally true rather than a rule someone has to remember.

| Instance | Database | Tables | Holds |
| --- | --- | --- | --- |
| shared | core | 6 | Accounts, passkeys, recovery codes, trusted devices, sessions, login events |
|  | community_vault | 15 | Personas, posts, replies, reports, blocks |
|  | clinical_vault | 11 | Journals, moods, stories, therapy records |
|  | billing_vault | 7 | Subscriptions, payments, subsidy allocations |
| identity (dedicated) | identity_vault | 11 | Real names, verified numbers, emergency contacts, break-glass cases |
| audit (dedicated) | audit_vault | 3 | Append-only, hash-chained event log |

### 3.2  Seventeen services behind one door

Every request enters through the privacy gateway and nothing reaches a service directly. The gateway runs a nine-stage pipeline — route policy, session, RBAC, consent, purpose limitation, rate limiting, data minimisation, audit, then forward. 25 API groups are declared in metadata; the gateway's entire routing and authorisation behaviour is derived from that file rather than written in code.

Audit is written before the request is forwarded, not after. That is the only arrangement that satisfies both rules at once: every access decision is recorded, and nothing is recorded that did not happen.

### 3.3  Technology decisions, settled

| Runtime | Node 26, TypeScript, pnpm workspaces + Turborepo |
| --- | --- |
| Sessions | Opaque tokens in Redis, not JWTs — so revocation is instant |
| Authentication | Phone + OTP, WebAuthn passkeys, recovery codes |
| Encryption | Envelope encryption per record; OpenBao Transit holds the keys |
| Service-to-service | HMAC-signed identity headers (mTLS before production) |
| A1 moderation | MuRIL-large, 506M parameters, self-hosted on the GPU |

### 3.4  Two mechanisms worth understanding

The audit chain. Every row carries the hash of the row before it. Tampering with any row breaks every hash after it, so the log can prove it has not been edited. A failed audit write fails the operation it was recording — an unrecorded access is treated as an access that must not happen.

Metadata as the source of truth. Route policy, plan quotas, consent purposes, audit event types and the handle vocabulary all live in schema-validated YAML. There are no hardcoded lists in code, which means a policy change is reviewable by someone who does not read TypeScript.

## 4.  What Is Actually Built

Four milestones complete. The numbers below come from the repository and the running stack.

| Component | State | Evidence |
| --- | --- | --- |
| Privacy gateway | RUNNING | 9 stages, 25 route groups, 38 tests |
| M0 Local infrastructure | COMPLETE | 3 Postgres instances, Redis, OpenBao; 17 migration and grant files apply cleanly from scratch |
| M1 Vault schemas | COMPLETE | 53 tables; 122 audit event types seeded (62 declared, 60 derived from route policy) |
| M2 Shared packages | COMPLETE | consent-policy-engine, audit-client, session-store, service-auth, shared-types |
| M3 auth-service + pseudonym-service | COMPLETE | Registration, passkeys, OTP login, recovery codes, permanent handles, trusted devices |
| M4 A1 served locally | NEXT | Model trained to a1-v11; orchestrator is scaffolding |

### 4.1  What M3 delivered, in detail

Three ways back into an account, each covering the failure of the one above it:

- Passkey — the member has their device. Real WebAuthn, verified against a virtual authenticator that signs with a genuine P-256 key rather than a stub.

- OTP — the device is gone, the number is not. Rate limited per number, not per session, so clearing cookies does not reset it.

- Recovery code — the number itself is gone. Deliberately requires no OTP, because that is precisely the situation it exists for. Single use, enforced by an atomic update.

Every failure across all three returns an identical response, so none of them can be used to discover whether a given handle or number has an account on a mental health platform.

Handles are permanent and always drawn. QuietRiver-4821. Members cannot choose their own, and that absence is the privacy property: a chosen name is almost always a name already used elsewhere, and reusing it here would tie everything written about a person's mental health to their public identity. The vocabulary is 200 × 200 words × 9000 numbers = 360 million handles, about 36× the membership target — which matters because a permanent handle is never returned to the pool, making the vocabulary a hard ceiling on total accounts.

Trusted devices are not credentials. A device grants nothing, skips nothing, and shortens no login. It exists so a member can see where their account is signed in and end a session they do not recognise. The stored identifier is scoped to the account — HMAC(pepper, accountId ‖ deviceKey) — so one physical phone produces a different hash for every account used on it, and the table cannot reveal that two pseudonymous accounts share a handset.

### 4.2  Verification that exists today

| 182 unit tests | gateway 38, auth-service 40, pseudonym-service 20, consent engine 42, session store 18, service-auth 16, audit client 8 |
| --- | --- |
| 39 privilege boundary checks | Proves each service can reach its own vault and cannot reach anyone else's, including across instances |
| 3 live end-to-end suites | Passkey flows, login and recovery flows (35 checks), device management (37 checks) — run against the real stack, not mocks |
| Audit integrity | Hash chain verified unbroken; no mobile number, device label or user-agent appears in any audit row |

## 5.  What Is Not Built

Stated plainly, because the directory structure makes the platform look more finished than it is.

- Fifteen of seventeen services are empty scaffolding — community, moderation, clinical vault, consent, care/therapy, therapist, billing/subsidy, safety/crisis, break-glass, identity vault, notification, retention, partner, admin, audit query. Directories and route policy exist; no code does.

- Fifteen of twenty shared packages are empty — crypto-client, pricing-engine, observability, i18n-core and others are declared but unimplemented.

- The AI orchestrator is scaffolding — ten files, most of them .gitkeep.

- OpenBao Transit is not configured. Envelope encryption columns exist in the schema; nothing writes to them yet.

- The frontend is not wired to the real API.

- The privacy test suite does not exist (tests/privacy/), nor does the data classification metadata. Both are named in the architecture.

- Six of the seven planned ADRs are unwritten. Only ADR-0001, on AI layer topology, exists.

## 6.  The A1 Classifier — Current Honest State

This is the item most likely to be misread, so it is stated exactly.

| Version | a1-v11, MuRIL-large (506M), full fine-tune |
| --- | --- |
| Training data | 58,014 examples; 7,431 held out for validation |
| Categories covered | 7 of 16 — bullying/harassment, hate speech, threats/intimidation, grooming/exploitation, passive-aggressive abuse, unsafe medical advice, scams/financial exploitation |
| Categories with no coverage | 9 of 16 — including self-harm encouragement, manipulation/coercion, sexual exploitation, stalking/doxxing, impersonation, help-seeking discouragement |
| Adjudicated | No |
| Evaluation gates passed | None |
| Production ready | No, per its own model card |

What this means for launch. Self-harm encouragement — the single category that matters most on a mental wellness platform — has no working detector. Until it does, the platform can be opened to a capped, adult, waitlisted group with human review behind it. It cannot be opened to school students, and it cannot be opened to the public.

Fixing it is a data problem, not an architecture problem. The pipeline, the model and the serving path are all sound; the category lacks adjudicated training examples. Estimated two to four months of focused work, and it remains the highest-value item on the roadmap.

## 7.  Milestones to First Local Run

### 7.1  The goal, defined precisely

One machine runs the whole platform. In a browser you can register with a phone number, create a passkey, post anonymously, watch the post be moderated by A1, receive an AI supportive response, receive a reply, write a journal entry, withdraw a consent, export your data and delete your account. Every sensitive step writes a row to the audit vault, and the privacy test suite passes.

That is a complete, honest vertical slice. Everything after it is breadth.

| M | What it delivers | Done when | Estimate |
| --- | --- | --- | --- |
| M0 | Local infrastructure — Docker Compose for three Postgres instances, Redis and OpenBao, with migration, grant and verification runners. | The gateway boots against it, resolves a session and writes an audit row. | COMPLETE |
| M1 | Remaining vault schemas plus registered audit event types. | 53 tables across six databases; an audit row inserts and joins its registered type. | COMPLETE |
| M2 | Shared packages: consent policy engine, audit client, session store, service auth, shared types. | One implementation of "may this actor read this record for this purpose" exists and is unit tested. | COMPLETE |
| M3 | auth-service and pseudonym-service. Phone, OTP, passkey, recovery codes, permanent handle, trusted devices. | You can register, sign in three different ways, and the gateway resolves your session. | COMPLETE |
| M4 | A1 served locally on the GPU behind the orchestrator, wired to the gateway. | A test string returns a real moderation verdict through the gateway, and the verdict is audited. | 3–5 days |
| M5 | community-service and moderation-service. Posting, replies, hidden-reply rules, plan quotas, reports, appeals, five-day expiry. | You can post, be moderated, and see replies. Quotas enforce. | 2–3 weeks |
| M6 | AI supportive response — a self-hosted open model generating one reply per post. | No post is ever bare. | 1 week |
| M7 | clinical-vault-service and consent-service. Journal, mood, per-record consent, envelope encryption. | A journal entry is written, encrypted, read back and its consent withdrawn. | 2 weeks |
| M8 | Frontend wired to the real API. Auth flow, composer, feed, dashboard against live services. | The browser talks to the backend. No mock data anywhere. | 2 weeks |
| M9 | retention-service. Export and deletion across every vault, cache and index. | Delete your account and the privacy test suite proves the data is gone. | 1 week |

Four of ten complete. Remaining estimate: roughly eight to ten weeks of focused work to the first local run, excluding the A1 data work in section 6, which runs in parallel and gates public launch rather than local completeness.

## 8.  Risks

| Risk | Standing |
| --- | --- |
| A1 cannot detect self-harm encouragement. | Open, and the binding constraint on public launch. Data, not architecture. See section 6. |
| 32 GB RAM ceiling. Three Postgres instances, Redis, OpenBao, six Node services, A1 on the GPU and a generative model for M6 is a tight fit. | Open. A1 sits in GPU memory, which helps; the M6 model must be quantised to share the 16 GB card. Expect to run services selectively rather than all at once. |
| Shared-secret service auth. An HMAC secret distributed to fifteen services is a weaker boundary than the network segment it protects. | Known and documented. mTLS between deployables is required before the identity vault holds real records. |
| OpenBao unconfigured. Encryption columns exist but nothing writes to them. | Open. Must land before M7, when the first genuinely clinical content is stored. |
| Solo maintainer. Every decision in this document has one person behind it. | Structural. Mitigated by the metadata-driven design and by the reasoning being written down beside the code rather than held in memory. |

End of document. Generated from a direct audit of the repository on 11 September 2026.